{"text_format":"1","workbook":"xlsx","n_sheets":2,"sheets":["SCPP - Supplier Rollout Plan","SCPP - Production Rollout Plan"],"not_rendered":{"charts":0,"images":1,"macros":0,"external_links":0,"defined_names":2,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"SCPP - Supplier Rollout Plan","index":0,"n_rows":47,"n_cols":61,"rows_kept":47,"cut":false,"hidden":false,"merged":[[26,1,26,2],[2,13,2,16],[2,9,2,12],[2,3,2,8],[4,1,4,2],[17,1,17,2],[20,1,20,2],[3,5,3,6],[2,26,2,29],[2,30,2,34],[0,1,0,34],[2,56,2,60],[2,35,2,38],[2,39,2,42],[2,43,2,47],[2,48,2,51],[2,52,2,55],[2,17,2,21],[2,22,2,25],[1,1,1,47]]}
[]
[null,"Rollout: Supply Chain Performance Program Purchasing"]
[null,"Location","Plant","2021-06-01",null,null,null,null,null,"2021-07-01",null,null,null,"2021-08-01",null,null,null,"2021-09-01",null,null,null,null,"2021-10-01",null,null,null,"2021-11-01",null,null,null,"2021-12-01",null,null,null,null,"2022-01-01",null,null,null,"2022-02-01",null,null,null,"2022-03-01",null,null,null,null,"2022-04-01",null,null,null,"May 22",null,null,null,"2022-06-01"]
[null,null,null,22,23,24,null,25,26,27,28,29,30,31,32,33,34,35,36,37,38,39,40,41,42,43,44,45,46,47,48,49,50,51,52,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26]
[null,"Europe"]
[null,"Schweinfurt","SWE"]
[null,"Höchstadt","HMS"]
[null,"Lahr","IWL"]
[null,"Steinhagen","ELG"]
[null,"Homburg","ILH"]
[null,"Herzogenaurach","IWS"]
[null,"Caldas da Rainha","FRC"]
[null,"Debrecen","FAH"]
[null,"Haguenau","ILF"]
[null,"Brasov","ISB"]
[null,"Kysucke","IWK"]
[null,"Skalica","ILS"]
[null,"Americas"]
[null,"Sorocaba","IB1"]
[null,"Joplin","FAJ"]
[null,"Asia / Pacific"]
[null,"Vietnam","SVC"]
[null,"Changwon","FHS"]
[null,"Pune","IBI"]
[null,"Baroda","FBI "]
[null,"Savli","SFI"]
[null,"Greater China"]
[null,"Nanjing","SNM"]
[null,"Yinchuan","FXR"]
[]
[]
[null,"Legend:  ",null,"Supplier information letter about Supply Chain Performance Program"]
[null,null,null,"Supplier web site available (with relevant information material)"]
[]
[null,null,null,"Supplier information letter about packaging data updates"]
[null,null,null,"Supplier specific info about missing packaging data sheets for each plant"]
[null,null,null,"Guideline how to fill out the packaging data sheet"]
[null,null,null,"Process description for the updates of packaging information"]
[]
[null,null,null,"Start query to get updated replenishment lead times (RLT) from all suppliers for all components"]
[]
[null,null,null,"Start SupplyOn integration (WebEDI/EDI; ASN; GTL; Performance Monitor)"]
[]
[null,null,null,"Rollout & signing of Industrial Supply Agreement*"]
[null,null,null,"Supplier specific component overview with new classification, expected delivery lead time, current & future fixed horizon"]
[null,null,null,"Training material for suppliers to understand details of the Supply Agreement are available (in Englisch and Chinese)"]
[null,null,null,"*) a supplier to multiple plants will typically be contacted only once (timing dependent upon the plant with the earliest need to get the Supply Agreement in place)"]

{"sheet":"SCPP - Production Rollout Plan","index":1,"n_rows":67,"n_cols":49,"rows_kept":67,"cut":false,"hidden":false,"merged":[[5,1,5,5],[33,1,33,5],[40,1,40,5],[55,1,55,5],[3,18,3,21],[3,6,3,9],[3,10,3,13],[3,14,3,17],[0,1,0,5],[3,44,3,48],[3,22,3,26],[3,27,3,30],[3,31,3,34],[3,35,3,39],[3,40,3,43]]}
[]
[]
[null,"Rollout: Supply Chain Performance Program per Plant/Segment"]
[null,"Plant","Location","Plant No.","Segment","Comment","2021-11-01",null,null,null,"2021-12-01",null,null,null,"2022-01-01",null,null,null,"2022-02-01",null,null,null,"2022-03-01",null,null,null,null,"2022-04-01",null,null,null,"2022-05-01",null,null,null,"2022-06-01",null,null,null,null,"2022-07-01",null,null,null,"2022-08-01"]
[null,null,null,null,null,null,44,45,46,47,48,49,50,51,1,2,3,4,5,6,7,8,9,10,11,12,13,14,15,16,17,18,19,20,21,22,23,24,25,26,27,28,29,30,31,32,33,34,35]
[null,"Europe"]
[null,"SWE","Schweinfurt","0200","Segment 04","completed"]
[null,null,null,null,"Segment 12","current plan"]
[null,null,null,null,"Segment 06","current plan"]
[null,null,null,null,"Segment 11","current plan"]
[null,"HMS","Höchstadt","0072","Segment 04","current plan"]
[null,null,null,null,"Segment 03","current plan"]
[null,"IWL","Lahr","0002","Segment 01","current plan"]
[null,null,null,null,"Segment 04","current plan"]
[null,"ELG","Steinhagen","0012","Segment 02","current plan"]
[null,"IWS","Herzogenaurach","0061","Segment 01","current plan"]
[null,"FRC","Caldas da Rainha","0254","Segment 02","current plan"]
[null,"FAH","Debrecen","0236","Segment 03","current plan"]
[null,"ISB","Brasov","0097","Segment 21","current plan"]
[null,null,null,null,"Segment 24","current plan"]
[null,null,null,null,"Segment 06","current plan"]
[null,null,null,null,"Segment 01","current plan"]
[null,null,null,null,"Segment 08","current plan"]
[null,null,null,null,"Segment 10","current plan"]
[null,null,null,null,"Segment 16","current plan"]
[null,null,null,null,"Segment 20","current plan"]
[null,"IWK","Kysucké Nové Mesto","0045","Segment 01","current plan"]
[null,"ILS","Skalica","0095","Segment 01","current plan"]
[null,null,null,null,"Segment 04","current plan"]
[null,null,null,null,"Segment 10","current plan"]
[null,"ILH","Homburg (Saar)","0009","Segment 01"]
[null,"ILF","Haguenau","0087","Segment 02"]
[]
[null,"Americas"]
[null,"IB1","Sorocaba","0701","Segment 32","preliminary plan"]
[null,"FAJ","Joplin","0275","Segment 01","preliminary plan"]
[null,null,null,null,"Segment 02","preliminary plan"]
[null,null,null,null,"Segment 04","preliminary plan"]
[null,null,null,null,"Segment 05","preliminary plan"]
[]
[null,"Asia / Pacific"]
[null,"SVC","Vietnam","0358","Segment 01","preliminary plan"]
[null,null,null,null,"Segment 02","preliminary plan"]
[null,null,null,null,"Segment 03","preliminary plan"]
[null,"FHS","Changwon","0297","Segment 06","preliminary plan"]
[null,"IBI","Pune","0042","Segment 02","preliminary plan"]
[null,"FBI","Baroda","0295","Segment 02","preliminary plan"]
[null,null,null,null,"Segment 04","preliminary plan"]
[null,null,null,null,"Segment 05","preliminary plan"]
[null,null,null,null,"Segment 08","preliminary plan"]
[null,"SFI","Savli","8210","Segment 01","preliminary plan"]
[null,null,null,null,"Segment 02","preliminary plan"]
[null,null,null,null,"Segment 05","preliminary plan"]
[null,null,null,null,"Segment 08","preliminary plan"]
[]
[null,"Greater China"]
[null,"SCT","Taicang","8101","Segment 24","Segment 24"]
[null,"SNM","Nanjing","8111","Segment 05","preliminary plan"]
[null,null,null,null,"Segment 06","preliminary plan"]
[null,null,null,null,"Segment 07","preliminary plan"]
[null,null,null,null,"Segment 10","preliminary plan"]
[null,null,null,null,"Segment 11","preliminary plan"]
[null,null,null,null,"Segment 42","preliminary plan"]
[null,null,null,null,"Segment 43","preliminary plan"]
[null,null,null,null,"Segment 45","preliminary plan"]
[null,null,null,null,"Segment 46","preliminary plan"]
[null,"FXR","Yinchuan","0289","Segment 02","preliminary plan"]